## Module Status
Sr | Module | Sub-Module | Definition Status | Development Status
1 | Platform Administration | Tenant lifecycle and provisioning | Defined | Not started
2 | Platform Administration | Feature flags and module enablement | Defined | Not started
3 | Platform Administration | Tenant plans, quotas, and entitlements | Defined | Not started
4 | Platform Administration | Tenant/company/mill hierarchy | Partially defined | Partially implemented
5 | Identity, Users & RBAC | Users and authentication | Defined | Partially implemented
6 | Identity, Users & RBAC | Roles and permissions | Defined | Partially implemented
7 | Identity, Users & RBAC | Server-side RBAC enforcement | Defined | Not started
8 | Identity, Users & RBAC | Segregation of duties | Defined | Not started
9 | Master Data & Configuration | Item/product master | Defined | Partially implemented
10 | Master Data & Configuration | Customers and suppliers | Defined | Partially implemented
11 | Master Data & Configuration | UOM and conversions | Defined | Partially implemented
12 | Master Data & Configuration | Vehicles, drivers, and transporters | Defined | Partially implemented
13 | Master Data & Configuration | Storage locations and tanks | Defined | Partially implemented
14 | Master Data & Configuration | Quality parameters and sampling plans | Defined | Partially implemented
15 | Sales & Customer Management | Customer management | Defined | Partially implemented
16 | Sales & Customer Management | Sales contracts | Defined | Partially implemented
17 | Sales & Customer Management | Customer orders and delivery commitments | Defined | Partially implemented
18 | Sales & Customer Management | Contract allocation and fulfillment | Defined | Planned
19 | Procurement & Supplier Management | Supplier management | Defined | Partially implemented
20 | Procurement & Supplier Management | Purchase/supplier contracts | Defined | Partially implemented
21 | Procurement & Supplier Management | Direct purchase | Defined | Partially implemented
22 | Procurement & Supplier Management | Commitment and supplier performance | Defined | Planned
23 | Weighbridge & FFB Receiving | Gate and vehicle entry | Defined | Partially implemented
24 | Weighbridge & FFB Receiving | Inbound weighbridge | Defined | Partially implemented
25 | Weighbridge & FFB Receiving | FFB receiving | Defined | Partially implemented
26 | Weighbridge & FFB Receiving | FFB grading and rejection | Defined | Partially implemented
27 | Weighbridge & FFB Receiving | Accepted/rejected reconciliation | Defined | Partially implemented
28 | Weighbridge & FFB Receiving | Receipt posting and reversal | Defined | Planned
29 | Inventory, Warehouse & Storage | Item and material lots | Defined | Partially implemented
30 | Inventory, Warehouse & Storage | Inventory ledger and balances | Defined | Planned
31 | Inventory, Warehouse & Storage | Reservations | Defined | Planned
32 | Inventory, Warehouse & Storage | Warehouse/storage areas | Defined | Partially implemented
33 | Inventory, Warehouse & Storage | Tank and storage capacity | Defined | Partially implemented
34 | Inventory, Warehouse & Storage | Transfers, reconciliation, and reversal | Defined | Planned
35 | Production Planning, Routing & MES | Production lines, stations, and machines | Defined | Implemented in prototype
36 | Production Planning, Routing & MES | Production routing and versions | Defined | Partially implemented
37 | Production Planning, Routing & MES | Production planning and scheduling | Defined | Partially implemented
38 | Production Planning, Routing & MES | Production runs and stage execution | Defined | Partially implemented
39 | Production Planning, Routing & MES | CPO, palm kernel, co-products, and waste | Defined | Planned
40 | Production Planning, Routing & MES | Mass balance, losses, genealogy, and inventory posting | Defined | Planned
41 | Quality Management | Quality parameters | Defined | Partially implemented
42 | Quality Management | Quality configuration/specifications | Defined | Partially implemented
43 | Quality Management | Production quality checkpoints | Defined | Partially implemented
44 | Quality Management | Quality observations and laboratory results | Defined | Partially implemented
45 | Quality Management | Evaluation, holds, and release | Defined | Planned
46 | Quality Management | Quality deviations and corrective action | Defined | Planned
47 | Sustainability, Mass Balance & Traceability | Certification and regulatory profiles | Defined | Not started
48 | Sustainability, Mass Balance & Traceability | Material genealogy and traceability | Defined | Planned
49 | Sustainability, Mass Balance & Traceability | Certified mass balance and claims | Defined | Not started
50 | Sustainability, Mass Balance & Traceability | Due diligence and evidence | Defined | Not started
51 | Maintenance, Equipment & OEE | Equipment and machine management | Defined | Partially implemented
52 | Maintenance, Equipment & OEE | Machine health monitoring | Defined | Partially implemented
53 | Maintenance, Equipment & OEE | Breakdown management | Defined | Planned
54 | Maintenance, Equipment & OEE | Preventive maintenance | Defined | Planned
55 | Maintenance, Equipment & OEE | Work orders and return to service | Defined | Planned
56 | Maintenance, Equipment & OEE | OEE and reliability reporting | Defined | Planned
57 | Dispatch & Delivery | Dispatch orders | Defined | Partially implemented
58 | Dispatch & Delivery | Loading and outbound weighing | Defined | Partially implemented
59 | Dispatch & Delivery | Quality clearance | Defined | Partially implemented
60 | Dispatch & Delivery | Stock issue and contract fulfillment | Defined | Planned
61 | Dispatch & Delivery | Delivery and proof of delivery | Defined | Planned
62 | Documents & Notifications | Document templates and numbering | Defined | Planned
63 | Documents & Notifications | Attachments and secure file access | Defined | Partially implemented
64 | Documents & Notifications | Notifications and escalation | Defined | Partially implemented
65 | Reporting & Dashboards | KPI definitions and formulas | Defined | Not started
66 | Reporting & Dashboards | Operational dashboards | Partially defined | Partially implemented
67 | Reporting & Dashboards | Reports and drill-down | Defined | Planned
68 | Reporting & Dashboards | Scheduled exports | Defined | Not started
69 | Integration Management | Weighbridge integration | Open decision | Not started
70 | Integration Management | Laboratory integration | Open decision | Not started
71 | Integration Management | Accounting/ERP integration | Open decision | Not started
72 | Integration Management | SCADA/PLC/sensor integration | Open decision | Not started
73 | Integration Management | Outbox, retry, and reconciliation | Defined | Planned
74 | Finance Interface | Sales invoicing | Defined | Partially implemented
75 | Finance Interface | Purchase invoicing | Defined | Partially implemented
76 | Finance Interface | Payments | Defined | Partially implemented
77 | Finance Interface | Accounting reconciliation | Open decision | Not started

## Legend
Status | Meaning
Implemented in prototype | Working prototype functionality exists, but enterprise hardening may still be required.
Partially implemented | Some screens, APIs, or domain rules exist; the full enterprise lifecycle is incomplete.
Planned | Defined in the target FRD/BRD but not yet implemented as a complete capability.
Not started | No dedicated implementation has been identified in the current repository.
Defined | Requirement/business rule is documented in the current baseline.
Partially defined | Some requirements exist, but the definition needs further refinement.
Open decision | Implementation depends on an unresolved product, process, compliance, or architecture decision.